## Sheet1
Question 1
Two Scrum teams are working on the same product. In the coming Sprints some of the Developers have realised that both teams are going to need the help of Chris, an external specialist who is the only person with the knowledge and authority to build the database environment. However, Chris is notoriously busy and has already said he can only spare enough of his time for one Scrum team per Sprint. What should the Scrum Master do? (choose 1)
Assign Chris to the team with the most urgent tasks first and then move him to the next team until the required support is completed.
Manage the items in the Sprint Backlogs so that Chris can be utilized evenly for each team.
Facilitate a discussion with all Developers from both teams on how they want to deal with this issue, and help them implement their preferred solution.
Ask Chris to help with recruiting additional database specialists. In the meantime, have the Product Owner prioritise the items that do not depend on Chris.
Resources
Q1 - External Specialist dependency
Question 2
What is the maximum time allowed between the conclusion of one Sprint to the start of the next? (choose 1)
There is no time between Sprints
Enough time to test the Increment
Enough time for the Product Backlog Refinement to get it ready for Sprint Planning
Resources
Q2 - Time between Sprints?
Domain
Scrum Events
Question 3
How often should the Scrum Team members change? (choose 1)
Never, as knowledge can be lost.
As needed, as long as it doesn’t impact productivity.
As needed, whilst taking into account a short-term reduction in productivity.
Frequently in order to be Agile
Resources
Q2 - Changing team members
Domain
Scrum Teams
Question 4
You join an established Scrum team as the new Scrum Master, you notice that the Product Owner has not been attending the Sprint Retrospectives. Through some investigation, you realise that the Developers don’t want to invite him fearing that he might make the Sprint Retrospective ineffective and even provide destructive criticism. As the new Scrum Master what should you do? (choose the best answer)
Respect the Developer's wishes as a self-managing team.
Work with the Developers to explore the problem and find a safe way to introduce the Product Owner to the Sprint Retrospective to enable greater transparency.
Speak to the Product Owner and see what he thinks. Do what they suggest is best.
Facilitate a discussion in the Scrum Team and allow them to decide what is best to do.
Resources
Q2 - PO not attending the Retrospectives
Domain
Facilitation
Question 5
How would you define Empiricism? (choose 2)
Making decisions based on predictions
Knowledge comes from theorising
Making decisions based on what is observed
Knowledge comes from experience
Resources
Q2 - How do you define Empiricism?
Domain
Empiricisum
Question 6
The Product Owner Josh regularly joins the Daily Scrum and tries to bring some encouragement by cheering and congratulating with cakes each time a Developer moves an item into the done pile. What should a Scrum Master do? (choose 1)
Take advantage of the chance to boost positivity by encouraging this behaviour of celebration for Done items.
Congratulate the Product Owner for promoting teamwork.
Coach the team about the purpose of the Daily Scrum and that working software is the primary measure of success.
Take no action. The Developers seem to be happy with this.
Resources
Q5 - Cheering Done items in the Sprint
Domain
Coaching and mentoring
Question 7
How do Timeboxes help a self-managing team? (choose the 2 best answers)
Developers can determine on their own how much overtime they should work to meet the timebox deadline.
Timeboxes encourage people to create the best possible result in the given time.
Timeboxes help everyone focus on the same problem at the same time.
Timeboxes shield the Developers from interruptions by the stakeholders and Product Owner.
Resources
Q3 - Self-management and timeboxes
Domain
Self-management
Question 8
3 Scrum teams are working in a Nexus on the same Product. At the Sprint Review, each team tells the Product Owner that their increments are ready for release but they show their Increments independently in different environments. Would this be cause for concern? (choose 1)
Yes
No
Resources
Q2 - Increments in the same environment
Domain
Scrum Artifacts
Question 9
You are a Scrum master for a Nexus team. Some of the developers in 2 Scrum Teams come to you with a risk that will soon become an impediment. The next Sprints will require a lot of commitment from Stacey, an external specialist who is not a member of the Scrum Team and cannot dedicate all her time to this product. What would you do? (choose the best 3 answers)
Developers with an interest in Stacey’s domain could volunteer to learn from Stacey and take on this work in their respective Scrum Teams.
Investigate whether additional techniques or frameworks for scaling Scrum would be appropriate for these Scrum Teams.
Create a team with Stacy and identify people from the Scrum Teams to temporarily work in Stacey’s domain to learn to better serve the existing teams.
Have the Developers work with the Product Owner to re-order the Product Backlog so Stacy can serve one team each Sprint.
Ask Stacy to help with hiring and training additional people, and for now, work with the Product Owner and Scrum Teams to re-prioritize the work so that tasks not depending on Stacey can be done first.
Resources
Q7 - Reliance on an external specialist
Domain
Self-management
Question 10
At Sprint Planning, three Developers get into an argument about the Sprint Plan. After an hour of raised tempers personal insults are exchanged. What should the Scrum Master do? (choose 1)
Defuse the conflict. By suggesting techniques to better plan work.
Conduct a session to help the Scrum Team resolve the conflict and create Sprint Plan. Remind the other members of the Scrum Team that conflicting ideas are to be expected, but they are accountable as professionals and should not make it personal.
End the discussion. Speak to the Product Owner and see if certain developers need to be removed from the team.
Take the people involved aside. Ask them to resolve the situation outside of the Scrum Team, if required through their managers.
Resources
Q6 - Team argument
Domain
Self-management
Question 11
You join a team as the Scrum Master and notice it is currently one single team of 15 developers and a Product Owner, what should you do? (choose 1)
Ask the department head to split the teams into less than 10 members per team
Suggest the team split into teams of 10 or fewer, facilitate the discussion on how to split the teams up
Insist the team splits and decide who works with who
Resources
Q5 - Too many Developers
Domain
Scrum Teams
Question 12
You are finding that Daily Scrums always take more than 15 minutes due to one of the more experienced developers going into a lot of depth about his work and issues the team is facing. What should you do? (choose 2)
Contact the team member's Line Manager and raise his ability to be concise as an issue.
You suggest passing a token around, where the person holding the token Is the only one allowed to speak and the rest will be listening to that person.
You ask the experienced developer how he sees his impact on the Daily Scrum, effectively coaching him into work better as an equal team member.
You remind the Developers that the Daily Scrum should take a maximum of 15 minutes and coach the Developers on how to be more efficient with their updates and that they can meet outside of the Daily Scrum to discuss what needs to be discussed.
You start using a timer and assign a timebox to each person to speak at the Daily Scrum and make sure that everyone has the opportunity to speak.
Resources
Q1 - Over running the Daily Scrum
Domain
Coaching and mentoring
Question 13
As a Scrum Master, which of the following would you do to make the Scrum Team more productive during the first Sprint? (choose all that apply)
Introduce the Scrum Team members to one another and provide a brief background on their talents and work history.
Allow the Developers to identify and discuss the procedure for converting the Product Backlog Items into a possibly releasable increment.
Allow the Product Owner to answer questions about the product, its history, goals, and context.
Suggest the team splits into a hierarchy of Developers with Senior Developers and Junior Developers.
Check that the Scrum Team members get along with each other.
Make certain that the Definition of Done is known and understood.
Resources
Q1 - Making the first Sprint productive
Domain
Scrum Teams
Question 14
The pillars of Empirical Process Control are: (choose 1)
Transformation, Inspection, and Adaptation.
Transparency, Inspection, and Adaptation.
Transparency, Iteration, Adaption.
Transparency, Investigation, and Adaption.
Courage, Openness, Commitment, Respect, and Focus.
Resources
Q5 - Pillars of Empirical Process Control
Domain
Empiricisum
Question 15
You have senior stakeholders that are very busy people. You invite them to the sprint reviews but they often do not attend. How does this affect empiricism and what might be the consequences? (choose 3)
Product Backlog prioritization decisions are made on limited information
Members who cannot attend the Sprint Review will have problems making product decisions
There are no tangible consequences
Decisions on the increment and how to adapt cannot be made
Key Stakeholders' feedback loop is too long risking high deviation
Resources
Q6 - Stakeholders not attending, the effect on Empiricism
Domain
Empiricisum
Question 16
One of the developers is disruptive and constantly disagrees with the team, this developer is slowing the decision-making progress and has started disregarding the team’s decisions and making his own decisions. What should you do as the Scrum Master? (choose the best 2 answers)
In a private conversation, you express your concern over his disagreements and tell him to comply with the team's decisions.
To anyone expressing this concern you suggest raising this with the entire team. You offer to help facilitate the conversation but not to resolve the concern yourself.
At the Sprint Retrospective, you wait to see if this topic is raised. If it does not happen, you raise it checking how everyone feels with the way team decisions are made.
You facilitate an out-of-work team-building event.
You raise this issue with the human resources department.
Resources
Q11 - Disruptive Developer
Domain
Self-management
Question 17
You are a Scrum Master of a team that has members working in different time zones around the world. Organizing the Scrum events is time-consuming and requires a lot of effort to set up and run. The Developers suggest only having the Daily Scrum every two days. Which responses would be most appropriate from yourself? (choose 3)
Point out that having less frequent Daily Scrums means less frequent opportunities to inspect and adapt introducing risk of undesired deviation from the Sprint Goal. The Sprint plan might become inaccurate with reduced transparency over progress toward the Sprint Goal.
Hold a vote and ensure that there is a consensus before reducing the Daily Scrum to every other day.
Coach the team on why having a Daily Scrum every day is an important opportunity to update the Sprint plan and how it helps the team self-organize work toward achieving the Sprint Goal.
Acknowledge and support their decision.
Help the team understand that lowering the frequency of communication will only increase the feeling of disconnect between the team members.
Resources
Q4 - Teams in different time zones
Domain
Scrum Events
Question 18
Which of the below statements is true about the Sprint Goal? (choose all that apply)
The use of Sprint Goals is optional because the Product Goal exists to guide development.
Sprint Goals often change during the Sprint as new insights emerge during working.
Sprint Goals give Developers flexibility and creativity on how to turn Product Backlog items into an increment of value.
It is the Scrum Team that crafts the Sprint Goal at Sprint planning, based on an objective the Product Owner would like achieved in that Sprint.
Resources
Q2 - What is true about the Sprint Goal
Domain
Self-management
Question 19
You need to put together four Scrum Teams with a Nexus team that will be developing a web application. The stakeholders expects one Increment at the end of the first Sprint. What would be your main advice as the Scrum Master of this team? (choose 3)
Each development team will have a Development Lead to coordinate the development work between the Scrum Teams
All Scrum Teams agree on a shared Definition of Done describing all the work needed to deliver an integrated increment for Sprint Review.
Teach them that it is their responsibility to form Scrum Teams with the skills and knowledge to create an Increment by the end of every Sprint.
It would be good to use only one Product Backlog for all the teams
It would be better to use the first Sprint to coordinate work and prepare the environments, and set things up. Increments can be delivered from the second Sprint onwards.
Each Scrum Team should deliver done increments from its own sprint. Each increment is shown in a separate environment at the Sprint Review, then the code is isolated for future stabilization.
Resources
Q3 - Making a Nexus
Domain
Scrum Teams
Question 20
How many Increments should there be per sprint… (choose 1)
It depends on the Sprint Goal
At least one
Just one
Resources
Q3 - How many increments per Sprint?
Domain
Scrum Artifacts
Question 21
The Product Owner wants to know what each Developer is working on every day and insists that the developers send a report to her daily based on the information from the Daily Scrum. As the Scrum Master what should you do? (choose 1)
Request that the Product Owner no longer attends the Daily Scrum.
Suggest the Product Owner look at the Sprint Backlog and burndown chart to report daily progress to the stakeholders.
Do nothing. The Product Owner needs to continue to track progress.
Coach the Product Owner and Developers on the purpose of Scrum Artifacts and Events and facilitate a discussion about their concerns and help them to find a solution to the root cause of the problem.
Resources
Q4 - Keeping Events true to their purpose
Domain
Coaching and mentoring
Question 22
When multiple Scrum teams are working from the same Product Backlog, how should the work be distributed between teams? (choose 1)
The Product Owner separates the Product Backlog items based on knowing the strengths of each team.
The Scrum Team with the highest capacity will choose what to work on first.
The Developers from each team pull in work from a shared Product Backlog in agreement with the Product Owner and the other teams.
Resources
Q8 - Work distribution between teams
Domain
Self-management
Question 23
The product owner has used the Scrum team’s velocity to estimate delivery in 3 months. This is the reported delivery date to customers and stakeholders that desperately need the new functionality. However, at the last Sprint Review, it has been discovered that the current increment did not work! At the Sprint Retrospective, some developers admitted they have not been adhering to all elements of the Definition of Done. What is the most effective way to recover by the deadline? (choose 1)
The Developers set the technical debt work aside to be performed in one or more hardening Sprints. They ask for more resource from other scrum teams to assist.
The team needs to restore transparency by adding the undone work to the Product Backlog. The Developers must figure out a way to deliver in the upcoming Sprints a greater velocity than they have previously been able to do. The Scrum Master monitors progress and if needed initiates a restart with a more reliable team or cancels the project.
The Developers inform the Product Owner that the progress she has perceived to date is not correct. The Increment is not releasable. They give a new estimate of the effort it would take to get the past work done, and suggest doing that work first before proceeding with new features. The Developers also re-estimate the effort to complete the remaining backlog, including all testing. In the end, it is Product Owner's call to continue the product or to cancel.
In the next Sprints, the Developers keep making sure that all of the selected scope per Sprint is as done as possible, at least at the past level of 85%. In every Sprint the undone work of the previous Sprint is estimated and added to the Sprint Backlog. The developers think they can complete all forecasted work.
Resources
Q5 - A velocity problem
Domain
Scrum Values
Question 24
A Scrum Team has been working together for 10 Sprints and the Developers have become quite mature as a team, working well together and have a good understanding of the product. A new Product Owner is appointed and doesn’t know much about the product or the company. What activities would you recommend that the Product Owner focuses on? (choose the best 2 answers.)
Advise the Product Owner to start building great relationships with the stakeholders and set up ongoing interaction with them. This will help the Product Owner maximise the value of the product in an environment of changing organizational or market expectations.
Tell the Product Owner to focus on the requirements and make sure there are no ambiguities or potential misunderstandings in the Product Backlog. Capture requirements in an analysis stage which would be considered the main output of an analysis Sprint.
You inform the Product Owner that the Developers need to be updated on changing business priorities daily. This is why there is a Daily Scrum meeting.
You advise the Product Owner to rely on the others in the Scrum Team and the stakeholders for amending the Product Backlog for now, but work closely with them to get up to speed as soon as possible. This is because they are the most knowledgeable about the market and the product for now.
Resources
Q3 - A new Product Owner
Domain
Coaching and mentoring
Question 25
You are one of 3 Scrum teams working on a product and your Sprints are one month long. Changes have been made to the company’s technical infrastructure that will cause extended testing for your increment. You are unable to deliver the increment in time for the other Scrum Teams that rely on your contribution to their increment. Also, the CEO is extremely unsatisfied with your team’s velocity on in this sprint. As a Scrum Master is the best thing to do? (choose 1)
You suggest working with the other scrum teams on the ordering and the value of your open Product Backlog items to redefine the possible delivery date.
You calculate how many additional developers it would take to increase velocity to make the original date. You inform the program manager of the additional budget for these developers.
You lengthen your Sprints to accommodate the delays.
You remove all items from the Product Backlog for which development is forecast to be beyond the expected date.
Resources
Q4 - Environment changes causes issues
Domain
Scrum Values
Question 26
One of the new developers feels left out of discussions and that his opinions are not considered. He brings this up at the Sprint Retrospective. What values are NOT being displayed here? (choose 3)
Courage
Openness
Respect
Commitment
Focus
Resources
Q3 - Developer is left out
Domain
Scrum Values
Question 27
Why might it benefit Empiricism to have shorter Sprints rather than longer Sprints? (choose all that apply):
Shorter Sprints allow for more opportunities to inspect and adapt
Shorter Sprints minimizes further deviation by frequent inspecting and adapting
Shorter Sprints mean more chances to adapt to changes in the environment
Shorter Sprints allow more time working and reduces the amount of time in meetings
Shorter feedback loops reduce the risk of deviating
Resources
Q3 - Shorter or longer Sprints?
Domain
Empiricisum
Question 28
Which Scrum Artifacts have commitments and when are they inspected? (Choose 3)
For the Sprint Goal, its commitment is the Definition of Done, inspected at the Daily Scrum.
For the Sprint Backlog, its commitment is the Product Goal, inspected at the backlog refinement session.
For the Sprint Backlog, its commitment is the Sprint Goal, inspected at the Daily Scrum.
For the Product Backlog, its commitment is the Product Goal, inspected at Sprint Planning and the Sprint Review.
For the Increment, its commitment is the Definition of Done, inspected at the Sprint Review
For the Sprint, its commitments are the Scrum Values and Empirical Pillars.
Resources
Q1 - When are Artifacts reviewed
Domain
Scrum Artifacts
Question 29
A highly respected and influential Developer often takes up a lot of time in the Daily Scrum by going off on tangents on things not so relative to the Sprint Goal. The Daily Scrum rarely finishes within 15 minutes. The other Developers dare not interrupt this Developer or ask him to stick to the topics in hand because the Developer is highly integral to the development of the product. As the Scrum Master has accountability to ensure the timebox is kept to 15 minutes, what should you do? (choose the best 2 answers)
You suggest passing a baton around. The person holding the baton can speak for 3 minutes only.
You suggest privately asking them what they believe the key outcomes for the Daily Scrum are. Effectively coaching them to help create focus during the Daily Scrum.
You suggest coaching the Developers to help them find a way to solve the problem, bringing this up in the Sprint Retrospective at the latest and ask the team to find a solution.
You contact the Developer’s Manager and raise this as an impediment to the Manager, and ask that they resolve this matter.
Resources
Q10 - One person taking too much time in the Daily Scrum
Domain
Self-management
Question 30
A Scrum Team decides to implement a semi-frequent "hardening and release sprint." What should a Scrum Master suggest? (choose all that apply)
Having a specific Sprint for hardening is a good idea, Scrum can be adapted to suit different situations.
The team should review the Definition of Done as it does not look like it is stringent enough to ensure a stable increment for release.
Hardening Sprints are supported by the Scrum framework so this is acceptable.
If a Sprint is needed to make the product stable then there is development debt to take care of.
Investigating if the team is adhering to the Definition of Done every Sprint.
Resources
Q6 - Hardening Sprint bad practice
Domain
Scrum Events
Question 31
At the moment, the engineering branch of your company is organized in siloed teams that specialize according to function (for example, design, front-end, back-end, database, and testing). What factors do you think are important to consider while transitioning from component teams to feature teams? (choose 2)
It is impossible to do Scrum without feature teams. Do not try to adopt Scrum until teams are reorganized into feature teams.
With feature teams, it is easier to calculate and compare the productivity per team. Incentives on productivity are likely to speed up the transition to feature teams and, therefore the adoption of Scrum.
Feature teams will require time to become productive as people from the different layers and components become accustomed to working and delivering unified functionality together as one Scrum Team.
Productivity, in terms of lines of code or story points, will probably suffer during the transition, although even then delivery of business value is still likely to increase.
Resources
Q6 - Siloed Teams
Domain
Scrum Teams
Question 32
During the Sprint Retrospective, the Product Owner raised a concern that the Developers only just met the Sprint Goal for the last Sprint. Developers think that the cause of the problem might be that some of them were working on other projects at the same time and that delayed the work. Which Scrum value were they not following? (choose 1)
Commitment
Courage
Focus
Respect
Openness
Resources
Q6 - Only just meeting the Sprint Goal
Domain
Scrum Values
Question 33
At the Sprint Retrospective the Scrum Team are addressing the quality difficulties that prevented completing an appropriate Increment at Sprint end. However, the Developments did indicate that they were able to accomplish a high velocity. Which two of these responses would you think their Scrum Master is best to take? (choose 2)
Acknowledge the hard work but remind the Developers that they need to improve in order to do even more in the next Sprint.
Agree and acknowledge the team’s hard work, so they will be motivated to do even more in the next Sprint.
Stress the value of working software over measured velocity
Facilitate a discussion on how to improve the quality to a level high enough for the Increment to be releasable, even if the measured velocity drops in the next Sprint.
Resources
Q3 - High velocity but Sprint Goal not met
Domain
Done
Question 34
A key and very senior stakeholder directly asks a particular developer to add a piece of functionality to the sprint backlog now as an urgent task, is it disrespectful to refuse to add the functionality immediately? (choose 1)
Yes
No
Resources
Q2 - Pressure from Stakeholder
Domain
Scrum Values
Question 35
How does Scrum apply Empiricism? (choose 3)
All the artifacts are immutable, they do not change for clarity.
Scrum Artifacts help with transparency.
The accountabilities are inspected and adapted in every event.
During each Scrum Event, decisions are made on one or more artifacts.
Scrum is based on Lean thinking, which is empiricism.
One or more artifacts are inspected in each event.
Resources
Q4 - How does Scrum apply Empiricism?
Domain
Empiricisum
Question 36
Which two items best describe what ‘done’ means? (choose 2)
Having an Increment of working software that is potentially releasable to the end users.
All the work completed within the current skills of the Developers.
All the work performed as defined in the Definition of Done.
All the work needed to prepare the Increment for testing.
Resources
Q6 - What does Done mean?
Domain
Done
Question 37
Once born, who in the Scrum team can update or change an increment? (choose 1)
The Developers
The Product Owner
The Scrum Master
Senior Developers
Release Management
Resources
Q4 - When an increment is born, and who can edit it?
Domain
Scrum Artifacts
Question 38
After a recent Sprint Review some of the stakeholders felt that the information presented was too fast and they didn’t get chance to go into the depth that they felt they needed to. The meeting had to finish because it ended at the end of the business day. The stakeholders ask the Scrum Master to hold a follow up Sprint Review and extend the future Sprint Reviews. What should the Scrum Master do? (choose 2)
Coach the Developers with time management techniques and how to present the key information the Stakeholders need.
Schedule the next Sprint Review an hour earlier so that the event can be extended if necessary.
Invite the stakeholders to a Sprint Review Part 2 meeting.
Coach the stakeholders to understand Scrum and that all events are timeboxed and should not be extended, however they will discuss the timebox of the Sprint Review in the Sprint Retrospective and see if it can be extended for future Sprints. In the meantime help the Scrum Team to interact more with the stakeholders throughout the Sprint.
Overall explanation
The Scrum guide says the Sprint Review "is timeboxed to a maximum of four hours for a one-month Sprint. For shorter Sprints, the event is usually shorter." As the Sprint should never be longer than a month, we can deduce that the maximum a Sprint Review should be is 4hrs. It is always best if the Scrum team can learn to manage time better and present key information in the time allotted. However, the Sprint Review is there to make improvements for future Sprints, so this situation should certainly be discussed. If the Sprint Review is too short and then it makes sense to make future ones longer, so long as they aren't so long that they break the Scrum Guide guidelines.
Resources
Q6 - Sprint Review too fast - a cross-functional team
Domain
Coaching and mentoring
Question 39
The Developers have realized that it does not possess the necessary tools and infrastructure to complete each of the items chosen from the Product Backlog. What action would you recommend as the Scrum Master? (choose 1)
Coach the Developers to improve its skills, tools and infrastructure over time and establish a Definition of “Done” that is actually possible to achieve given the current circumstances.
Stop the Sprint and have the Developers work on the infrastructure before continuing.
Encourage the Product Owner to accept partially done Increments and complete the work in the Hardening Sprint.
Resources
Q7 - When the developers don't have the skills and tools
Domain
Coaching and mentoring
Question 40
What is the first event of the Sprint? (choose 1)
Daily Scrum
Backlog Refinement
Sprint Retrospective
Sprint Planning
Sprint Review
Resources
Q1 - First Event of the Sprint
Domain
Scrum Events
Question 41
How should a Scrum Master divide a group of 50 people into multiple scrum teams? (choose 1)
Ask the developers to divide themselves into teams.
Create teams based on the functional layer they are working on.
Create teams based on the health of the working relationship of the team members.
Resources
Q4 - Splitting a big group into Scrum Teams
Domain
Scrum Teams
Question 42
Developing new or revising existing technical documentation is a requirement of the team's Definition of Done. This is done to ensure that the product and/or its features can be maintained in the future. During the Sprint, the team's technical writer will be on holiday. What action should you take? (choose 1)
Delay the documentation for the technical writer’s return and create a backlog of work to be handled in one technical writing sprint.
The Scrum Team is still accountable to meeting the Definition of Done, the Developers should write the documentation, they are best placed to do so as the developers of the product.
Tell the developers to form a specialist team of technical writers to work on documentation for this product and any others in the company.
Resources
Q8 - Documentation in the Definition of Done
Domain
Done
Question 43
What is the best description of the Definition of Done? (choose 3)
At Sprint Planning it guides the Developers when creating a forecast for items.
It creates transparency of the state of the Increment for inspection at the Sprint Review.
It serves as a checklist to inspect whether the Developers have performed all their tasks by the Sprint end.
It helps the Developers identify the work remaining for an Increment to be ready for release.
It serves to track how much of a Product Backlog item is completed during the Sprint.
Resources
Q1 - Description of Definition of Done
Domain
Done
Question 44
What questions should be answered during the Daily Scrum? (choose 1)
What did I do yesterday and what do I plan to do today?
None of these questions.
Both of these questions.
Do I see any impediment that prevents the Developers or me from meeting the Sprint Goal?
Resources
Q3 - Daily Scrum Questions
Domain
Scrum Events
Question 45
By the end of the Sprint, a Product Backlog item in the Sprint Backlog does not meet the team's Definition of Done. What two things should happen with the item? (choose 2)
Review the item, add the done part to the Increment. Estimate the remaining work and add that to the Product Backlog.
It will be inspected at the Sprint Review and if it is acceptable by the stakeholders then include it in the Increment.
Do not include the item in the Increment for the Sprint.
Estimate the remaining work needed to make it "done" and add it to the Product Backlog for the Product Owner to decide what to do with it.
Resources
Q7 - What to do if Definition of Done is not met
Domain
Done
Question 46
During a Daily Scrum 2 developers disagree on a task and get into a heated argument, what Scrum Value are they not showing? (choose 1)
Courage
Respect
Openness
Focus
Commitment
Resources
Q1 - A heated argument
Domain
Scrum Values
Question 47
You are a Scrum Master of a 9 member Scrum Team; you haven't joined the Daily Scrum for some time because you thought it was running well. However, you join today and notice it took 20 minutes. The Developers often go over 15 minutes and they propose dividing the Scrum Team into two cohesive groups with their own Daily Scrum. What is your response? (choose 1)
You agree. If the Daily Scrum becomes too long, the team should consider reorganizing into multiple cohesive Scrum Teams, each focused on the same Product and Product Backlog.
You offer to join the Daily Scrum and teach them to keep the Daily Scrum within a 15-minute timebox.
You say that it is common and reasonable to extend the Daily Scrum. The 15 minute rule is just a guideline.
Resources
Q7 - Daily Scrum running over
Domain
Scrum Values
Question 48
The Product Owner is concerned about the slow progress of releases and thinks the Definition of Done should be reduced to speed up progress. As the Scrum Master what would you advise? (choose 4)
Advise seeking the stakeholder’s permission by informing them that reducing the Definition of Done will lead to more frequent releases and greater velocity.
Accept the decision as a mutual agreement has been made between the Developers and the Product Owner.
Reducing the Definition of Done will introduce technical debt such as unknown errors as functionality is added. The product might become more difficult to stabilize as work progresses. Development for future releases is likely to be slowed down in unpredictable ways.
Releasing the version with a reduced Definition of Done creates false assumptions about the actual state of the system and is risky. Fixes may need to be added post-release impacting user experience, reputation and development progress.
Ask the Developers and the Product Owner what problem they are trying to solve by reducing the Definition of Done. In what ways will this decision impact transparency and quality?
Ask the Developers and the Product Owner if they are still able to produce releasable Increments by altering the Definition of Done.
Resources
Q4 - Reduction of Definition of Done bad practice
Domain
Done
Question 49
In Scaled Scrum should Scrum teams working on the same Increment have the same Start and End date? (choose 1)
No
Yes
Resources
Q9 - Scaled Scrum start and end dates of Sprints
Domain
Self-management
Question 50
During a Daily Scrum 2 developers disagree on a task and get into a heated argument, what are the best things a Scrum Master should do? (choose the 2 best answers)
Help create the environment and space to discuss conflicts, find agreements in a productive and positive way. Remind the other members of the Scrum Team that conflicting ideas are natural, but making it personal does not help.
Don't handle problems for the team. Instead, assist them in identifying and resolving issues on their own.
Try to move the team members away from each other to avoid further conflict as soon as possible to be productive.
Talk with each team member to understand why they have differences. Report them to their managers if they cannot solve their differences.
Wait till the Sprint Retrospective and show the importance of not wasting time in conflict, concentrating on work, and improving performance.
Resources
Q5 - Self-management to solve team disagreements
Domain
Self-management
Question 51
The Sprint Review often overruns resulting in many stakeholders needing to leave before the end of the meeting and missing key information. The stakeholders request to have a follow-up meeting the next day. As a Scrum Master how would you handle this situation? (choose 2)
Coach the stakeholders to understand Scrum and that all events are timeboxed and should not be extended.
Coach the Developers with time management techniques and how to present the most valuable functionalities first.
Split the Sprint Review into 2 parts and continue the Sprint Review the next day.
Schedule the Sprint Review an hour earlier than usual so that the event can be extended if necessary.
Coach the Product Owner to send an email to the stakeholders with a list of items that have been "Done" and what has not been "Done" before the Sprint Review to save time.
Resources
Q2 - Over running the Sprint Review
Domain
Coaching and mentoring
Question 52
Should the Definition of Done include testing? Choose the best answer
Yes testing is mandatory to ensure the increment is ready to be released.
It’s not mandatory, it’s up to the organisation and the Scrum team to decide on the Definition of Done.
Resources
Q9 - Should the Definition of Done include testing?
Domain
Done
Question 53
When it comes to completing all the items in the Sprint Backlog, all the Product Backlog Items added to the Sprint Backlog must be done by the end of the Sprint? (choose 1)
FALSE
TRUE
Resources
Changing Defo of Done & Q5 - Should all items be done by Sprint End?
Question 54
You have a choice of ways and locations to hold the Daily Scrum, how do you decide what option is best? (choose 1)
It should be held in a secluded area of the office so not to disturb others.
It should be held in a room where management cannot overhear.
It should be held wherever the Developers think is best.
It should be held wherever you can get on that particular day.
It should be held around the Scrum board.
Resources
Q7 - Who chooses the Daily Scrum location?
Domain
Scrum Events
Question 55
What is Scrum Based on? (choose 2)
A Defined Process
Lean thinking
A Hybrid Model
Empiricisum
A Complex Process
Resources
Q1 - What is Scrum based on?
Domain
Empiricisum
Question 56
After discussions you as the Scrum Master have convinced them that they need to have the Daily Scrum every day, but this still does not solve the problem of the trouble in hosting these meetings. As the Scrum Master what should you do? (choose the best answer)
Mandate the use of tools used elsewhere in the organisation that have helped other teams who are in different locations
Divide the Developers into subteams per location.
You as the Scrum Master are responsible for setting up the meetings.
Bring up the topic for discussion and allow the Developers to determine for themselves what to do as a self­ managing team.
Cause the removal of this impediment by informing management and challenge the distributed nature of the team
Tell the Developers to alternate who attends.
Resources
Q5 - Where to have the Daily Scrum
Domain
Scrum Events
Question 57
It's important that product development teams be cross-functional and comprised of people with a wide range of expertise to succeed. When implementing Scrum, what are the benefits of maintaining the existing component teams (for example, design, database, backend, and frontend)? (choose 1)
Component teams would have all the skills needed to deliver an increment of value
Because they have been working together for some time, there will be less initial disruption than a newly formed team. As they begin working, they will discover what works best and how to move towards cross-functional teams
There is less communication overhead than working in feature teams
Because their productivity is already predictable, they can deliver more valuable Increments than a newly formed team
Resources
Q7 - Component team short term pros
Domain
Scrum Teams
Question 58
Who plans the work during the Sprint? (choose 1)
The Developers
The Scrum Master
The Product Owner
The Senior Developers
Resources
Q1 - who plans the work?
Domain
Self-management
Question 59
You are a Scrum Master for three Scrum Teams who are all working on the same Product. Management wants to measure the velocity of all three teams so that they know which teams are working well and which teams may benefit from more assistance. What are your best responses? (choose 2)
Standardizing velocity across teams is a good way to understand which teams are producing the most value.
Providing incentives based on velocity can increase the Scrum Team’s motivation to produce more value.
Velocity is the amount of business functionality that a particular Scrum Team creates in a Sprint. It is unique to that team and used to forecast work in Sprint Planning.
There is no direct relationship between velocity and value. Value of the increment to the stakeholders is measured in other ways.
Resources
Q2 - Proper use of velocity
Domain
Done
Question 60
Which of these answers is a good sign the team is self-managing. (choose the 2 best answers)
The Developers are able to resolve internal conflicts between members in order to continue working.
The Developers are cross-functional and know what they need to do to complete all tasks committed to in Sprint Planning
Management is able to know which members are working on which items.
Creativity thrives and new possibilities are explored.
Resources
Q4 - Signs a team is Self-managing
Domain
Self-management