## Sheet1
Question 1
A sensitive data breach has occurred with the live product, this is a disaster for the product, the company and the users. Immediate changes have to be made including adding more security tests and functionality to the Definition of Done. What should the team do? (choose 2)
A complete list of security-related Product Backlog items needs to be created before starting a new Sprint.
Increments should be fixed in parallel Sprints so as not to disrupt the release of new features. After the security concerns have been fixed, they will be applied to the work that is already in progress for new features.
The additional security requirements are added to the Product Backlog and addressed by the Product Owner to prioritize.
During the Sprint Retrospective, the Developers assess how to add these additions to their Definition of Done so every future Increment will meet these security requirements.
Resources
Q6 - Risk with the Product and emergency changes
Domain
Managing technical risk
Question 2
Are stakeholders only allowed to meet with the Scrum team at the Sprint Review? (choose 1)
No
Yes
Resources
Q5 - When can the Scrum Team meet the stakeholders?
Domain
Stakeholders and Customers
Question 3
What is the relationship between technical debt and delivery? (choose all that apply.)
Technical debt is allowed within certain limits.
A Product with a lot of technical debt may be unstable.
Technical debt should be a concern of the Scrum Team.
The more technical debt there is, the more difficult it is to maintain and add to the product.
Developers are responsible for making technical debt transparent and sharing the true product status and risk with the Scrum Team.
Resources
Q9 - The relationship between delivery and technical debt
Domain
Managing technical risk
Question 4
A Project Manager would like to use Scrum for a new project and comes to you for advice. After explaining the Scrum Framework he expresses his intention to skip the Daily Scrums favouring weekly meetups as his employees already meet every day. What would you advise? (choose 1)
During the Daily Scrum, the team members will discuss important technical solutions.
The Daily Scrum is necessary to update the Scrum board with the team's progress.
The Daily Scrum will keep the senior managers up to date.
If the team members meet in other meetings, it is actually fine to skip the Daily Scrum
Daily Scrums eliminate the need for other meetings.
Resources
Q1 - Coaching others to keep to the Scrum framework
Domain
Organizational Design & Culture
Question 5
When multiple Scrum Teams are working on the same Product it’s important that they all work on the same Product Backlog? (choose 1)
TRUE
FALSE
Resources
Q4 - Multiple teams same Product Backlog?
Domain
Product Backlog Management
Question 6
What should the Developers do if whilst working they realize mid-sprint that development is more complex than they forecasted and they have chosen too much work to do after starting the Sprint? (choose 1)
Work with the Product Owner to remove some work or Product Backlog items as soon as possible, whilst considering the impact on the Sprint Goal.
Continue working and update the Product Owner at the Sprint Review.
Add additional team members to handle the extra work.
Modify the Definition of “Done” to ensure all Product Backlog items can be done by the end of the Sprint.
Resources
Q10 - Yikes, the development is more complex than anticipated
Domain
Product Backlog Management
Question 7
You are 10 Sprints in and you observe that the Developers are hardly collaborating. Instead, the Developers are working in silos on their own tasks. You also notice that the items on the Sprint Backlog are mostly unrelated. You also notice that there isn’t a clearly defined Sprint Goal. The Product Owner and Developers inform you that due to the wide variety of items on their Product Backlog, creating a single Sprint Goal is not possible. What might explain why this Scrum Team is struggling to craft a Sprint Goal? (choose all that apply)
Scrum might not be the best framework for the work done by this team.
The Product Owner is not successfully communicating the Product Goal that they want to achieve.
The Product Owner is not empowered to make decisions about items on the Product Backlog or their prioritisation.
The Sprints are too long.
The Scrum Team is too big.
Resources
Q4 - Developers working in silos risk
Domain
Managing technical risk
Question 8
It takes a few Sprints before a major stakeholder begins utilizing the product. The unsatisfied stakeholder contacts the Product Owner to express concerns about the unsatisfactory performance. The Product Owner seeks guidance from the Scrum Master. What would you recommend? (choose 1)
Wait until the next Sprint Retrospective as it is the most opportune time to modify the Definition of Done.
Encourage the Product Owner to bring the performance concerns to the Developers and work with them on how to improve performance, and ultimately have a stronger Definition of Done.
Explain to the Product Owner that it’s up to the Developers to decide on acceptable performance standards as they own the Definition of Done.
Bring the concern to the testers and ask them to include performance testing.
Resources
Q6 - Unsatisfied stakeholders
Domain
Stakeholders and Customers
Question 9
During the Sprint, the Developers realizes they might not be able to finish all of the items in the Sprint Backlog. As the Scrum Master what would you suggest? (choose 1)
The Developers cancel the Sprint because they will not be able to meet the Sprint Goal.
Continue Sprinting until the work is complete and redefine a new Sprint based on the results of the current Sprint.
The Sprint length holds and the Developers continuously learn what is actually possible to do within the Sprint timebox.
Resources
Q13 - Can't finish all the items in a Sprint
Domain
Product Backlog Management
Question 10
A Scrum Team just released the first iteration of the Product, great news, it has been a success. The board want to speed up development and have allocated more budget to bring in 2 new Scrum Teams to work on the product. What would be the biggest concern for the current Developers? (choose 1)
How to reduce dependencies between teams?
Who will be a part of each team?
Which team will work on the front end and which team will work on the backend?
Who will be the Scrum Master?
Resources
Q5 - Bringing in an additional team concerns
Domain
Product Backlog Management
Question 11
The Product Owner is under pressure to release key features in 2 sprints time, ahead of competitors in the market and capitalising on this window of opportunity. The Developers do not think this is possible due to past reliance on external teams in the company that have been unreliable in the past. As the Scrum Master what do you suggest? (choose 1)
You determine how many extra developers would be required to increase velocity to meet the original deadline.
You reduce the length of your Sprints to deliver sooner.
You deprioritize any items from the Product Backlog which are projected to take longer than expected.
You propose working with the other team’s Developers to reduce dependencies and discuss reliability for this crucial release date.
Nothing, you can only estimate one Sprint at a time.
Resources
Q6 - Pressure to release
Domain
Product Backlog Management
Question 12
Which Product Backlog items can be considered ready for a Sprint? (choose 1)
Product Backlog items that can be done within one Sprint
Any Product Backlog Item
Product Backlog items that are estimated
Product Backlog items that are estimated, with a value and description
Product Backlog items that meet the Definition of Ready
It is up to the Product Owner
Resources
Q1 - How are items considered ready for Sprint Planning?
Domain
Product Backlog Management
Question 13
At the eleventh Sprint Review, the stakeholders are very disappointed. They say the product so far will not meet their needs and is going to cost more than they budgeted for. What might have led to this? (choose the best 3 answers)
Changes to the project plan were not adequately documented and shared. The change request procedure was not diligently followed.
The stakeholders were not allowed to enter the development area, and were not present at the Daily Scrums.
The Scrum Master has not ensured transparency.
The Product Owner has not been interacting frequently with the stakeholders and kept them aware of the progress of the project.
The stakeholders have not been using the Sprint Reviews to actively engage, and inspect and evaluate progress.
Resources
Q2 - Disappointed stakeholders
Domain
Stakeholders and Customers
Question 14
How much time should be spent refining the Product Backlog? (choose 2)
As much as the Scrum Team agrees is necessary to create enough ready Product Backlog Items.
Up to 10% of the capacity of the Developers in a typical Sprint, but as much as 90% in early Sprints.
The Scrum Team decides how and when refinement is done. The Product Backlog items can be updated at any time by the Product Owner or at the Product Owner’s discretion.
At least one Product Backlog refinement session should take place each sprint.
No more than 10% of the capacity of the Scrum Team.
Resources
Q2 - How much time should be spent on backlog refinement?
Domain
Product Backlog Management
Question 15
As the Scrum Master what advice would you give to the Product Owner when ordering the Product Backlog? (choose 1)
Delegate the work to the Assistant Product Owner. Delay the Sprint in order for the Product Owner to have enough time to prioritize the Product Backlog.
Offer the Product Owner help in understanding that the goal of ordering the Product Backlog is to maximize the flow of value.
Have the Product Owner order the items based on size, having the Developers work on the smallest items first for quick velocity.
As the Developers are closest to the work and doing the work, have them order the work instead of the Product Owner.
Resources
Q3 - Ordering the Product Backlog
Domain
Product Backlog Management
Question 16
If the Product Owner asks your opinion as the Scrum Master as to who the most important stakeholder is, how would you respond? (choose 1)
The Product budget holder
The company owner
The Product’s users
Any stakeholder on the board of directors
Resources
Q4 - Who is the most important stakeholder?
Domain
Stakeholders and Customers
Question 17
During the Sprint Review, the topic of budget was brought up and the project's budget may be cut owing to recent market developments. This causes the atmosphere to become tense, which in turn leads to disputes breaking out between people. What are the two most important things for the Scrum Master to do? (choose 2 best answers.)
Inform everyone that the team needs to stay busy until it is confirmed the team and Product is not needed anymore.
Be objective and request for a short break for people to calm down.
Encourage the stakeholders and Product Owner to focus on delivering the highest-value items for the next Sprint.
Defend the original budget and request the stakeholders adhere to the original agreed funding for the product.
Avoid getting involved as it is the Product Owner’s responsibility to manage stakeholder expectations.
Resources
Q1 - Budget cuts
Domain
Stakeholders and Customers
Question 18
The Product Owner decides to release the current Increment to production. The stakeholders ask to stop “Sprinting” to react more quickly to the user feedback that is expected after this release. As the Scrum Master, what would you advise? (choose the best 2 answers)
Continue sprinting but allow customer feedback to change the Sprint Goal within the Sprint.
Stop sprinting and let the Developers work on new customer requests as they arise.
Continue sprinting but shorten the Sprint length to allow for shorter feedback loops.
Continue sprinting and include the customer feedback in the Product Backlog.
Resources
Q1 - Feedback after a major release
Domain
Managing technical risk
Question 19
There is a new addition to the Developers, her name is Hilda. She is very creative and whilst developing she added new features to the increment that were not on the Product Backlog. This is discovered on the day of the Sprint Review. What should be done about these new features? (choose 2)
Developers report the problem to the Scrum Master, to take actions against Hilda
Hilda should ask the Product Owner to add this feature to the Product Backlog because it is already part of the Increment
Discuss the Scrum Framework and reasons for the Product Backlog in the Sprint Retrospective
If possible, the Developers should remove the feature from the Increment before the Sprint Review
Resources
Q9 - How to handle items added from outside of the Product Backlog
Domain
Product Backlog Management
Question 20
What is likely to happen if an organization only changed their current project terminology to fit Scrum without the proper understanding of Scrum as defined in the Scrum Guide? (choose all that apply)
Organizations may feel less stressed as the behaviours would remain familiar to management.
Confusion will arise between those that understand Scrum and those that don’t.
Very little change will happen as Scrum is more than a set of terminology.
The organization may not realize the real benefits of Scrum as there would be no real change on the way the teams work.
Resources
Q2 - Not applying Scrum properly
Domain
Organizational Design & Culture
Question 21
Your Scrum team has been working on a Product for 6 months. The product passes usability test and delivers an increment at the end of each Sprint, however it has not yet been released to real users. The stakeholders are putting a lot of pressure to release next month. The Product Owner does not think this is viable because the their is still a lot of work required before he has confidence in a release. He has a delivery date of 6 months and has been working towards that. What guidance or assistance can you provide by the Scrum Framework? (choose 3 answers.)
Challenge the Product Owner to validate if all the pending work is needed to release and how the number of features in a product release can be reduced.
Suggest the Product Owner meet with the team and rescope the scheduled work. Find out what can be released in one month to match the stakeholder's demands.
Inform the Product Owner that the whole organization must respect his judgments. Maintain the present product vision and six-month timeline.
Advise adding more teams to work on the product.
Encourage the Product Owner to interact with the Stakeholders to validate how much the current product satisfies their needs and the minimal things to add to release it.
Resources
Q12 - Product Owner delaying release
Domain
Managing technical risk
Question 22
What things are best considered when deciding on the Sprint length? (choose 1)
The level of expertise over the technology to be used, ability to release an Increment to the end users, and the risk of being disconnected from the stakeholders.
How often team membership changes and the size of the team.
Having consistent Sprint length across all Scrum Teams in the Nexus.
Resources
Q2 - Things to consider to decide the Sprint length
Domain
Managing technical risk
Question 23
Considering the Product Owner, which of the following will be a risk for the success of the Product Owner? (choose 1)
Sharing responsibilities with another Product Owner when overloaded.
Repeating the Product vision and goals to the team often.
Frequent interactions with the Stakeholders.
Autonomy on Product Backlog management.
Having to clarify Product Backlog Items although expectations are written.
Resources
Q3 - Product Owner bad practice risks
Domain
Managing technical risk
Question 24
What is the relationship between velocity and technical debt? (choose 2)
Estimating the technical debt and using the past velocity will help to predict when the project can be delivered.
When the Developers run into technical debt, the velocity will likely drop in the future.
They are not related. Technical debt does not affect velocity.
The Velocity measures the amount of technical debt to be fixed.
Allowing technical debt for a few Sprints artificially increases the velocity.
Resources
Q8 - The relationship between velocity and technical debt
Domain
Managing technical risk
Question 25
The Product Owner is under great pressure to release certain functionalities as soon as possible. To accelerate development, the Product Owner removes certain testing aspects temporarily from the Definition of Done. However, the Product Owner adds the missing testing to the Product Backlog to be done in the future. The Developers warn that this will increase technical debt. (choose the best 2 answer)
As long as the increment isn’t released before the testing is done this is acceptable to get the increment to Sprint Review. The Definition of Done can be reduced temporarily.
Unknown issues will grow as work develops and functionality is added to the reduced Definition of Done. Stabilization of the system becomes increasingly challenging. Work on the current release and future releases will be slowed in unanticipated ways.
The Product Backlog item must include a precise calculation and estimation of the technical debt resulting from reduced testing so that the overall amount of additional work can be forecasted and planned for.
Releasing with a reduced Definition of Done leads to incorrect assumptions about the product’s current condition. This is likely to cause unanticipated difficulties in future increments caused by not meeting the Definition of Done.
This approach is fine if you also schedule in a Technical Debt fixing Sprint after the release.
Resources
Q10 - Pressure to release and missing testing
Domain
Managing technical risk
Question 26
Can the Sprint Backlog items be changed mid-sprint? (choose 1)
No
Yes
Resources
Q8 - Can Sprint Backlog items be changed mid-sprint?
Domain
Product Backlog Management
Question 27
If the Technical Debt builds up, false assumptions about the present status of the Product and the Increment examined at Sprint Review might be made. (choose 1)
FALSE
TRUE
Resources
Q7 - Technical debt building up
Domain
Managing technical risk
Question 28
What should you advise a Developer to do if he/she is approached by a key stakeholder and pressures the Developer to add a “very important” item to the current Sprint? (choose 1)
Add the item to the top of the next Sprint Backlog.
Inform the Product Owner so he/she can work with the person.
Replace an item in the current Sprint of equal size.
Add the item to the bottom of the Sprint Backlog.
Resources
Q3 - Pressure from a key stakeholder
Domain
Stakeholders and Customers
Question 29
Anne is a Product Owner who needs to inform the board when the next release of a product is likely. With the Developers she considers the items in the Product Backlog needed to develop the Increment for the next release. Based on the team’s velocity she predicts the next release will be possible in 3 Sprints time. However the Developers admit to skipping some integration tests and believe that extra tests should be added to the Definition of Done before release. They believe it will take a further 10% of Sprint time to include these additional tests and believe that the release in 3 Sprints is still possible. What is the most effective way to recover? (choose 1)
The Developers set the open work aside to be performed in one or more “catch-up” Sprints. They inform Anne that they need more time, It is Anne’s responsibility to inform users and stakeholders of the impact on the release date.
Transparency needs to be restored by adding the undone work to the Product Backlog. The Developers must figure out a way to deliver in the upcoming Sprints their current velocity plus 3 more units of work to catch up on development debt. It is the Scrum Master's duty to assess whether such repair is possible. If not, then Anne will have to restart the project potentially with a different team and will have to inform the board and the stakeholders.
The Developers inform Anne that the progress she has perceived to date is not correct. The Increment is not releasable. They give Anne their estimate of the effort it would take to get the past work done, and suggest doing that work first before proceeding with new features. The Developers also re-estimate the effort to complete the remaining backlog, including all integration tests. In the end, it is Anne’s call to continue the project or to cancel.
The undone work of the previous Sprints is estimated and added to the Sprint Backlog. For the next 3 Sprints this development dept is considered and added to the Sprint Backlogs, through considering past velocity taking this approach seems achievable to have the release ready in 3 Sprints time. Anne reassures the board.
Resources
Q11 - Trying to predict the next release on bad information
Domain
Managing technical risk
Question 30
What can you do to ensure the Developers understand the Product Backlog items discussed at Sprint Planning? (choose 1)
Request a business analysts to help explain the high-priority items in the Product Backlog.
Having a separate group of Developers to dedicate full time to helping the Product Owner add new items based on their development expectations.
Request the Developers use some time during each Sprint to be involved in Backlog Refinement, helping the Product Owner decompose the items that are prioritised.
Resources
Q12 - How to ensure the Developers understand the Product Backlog items
Domain
Product Backlog Management
Question 31
At the Sprint Retrospective, you decide on 3 highly impactful changes to make. What should you do? (choose 2)
Address them as soon as possible
Record them in the Retrospective decision log
Add to the next Sprint Backlog
Add them to the Product Backlog
Ask the Scrum Master when and how to implement them
Resources
Q11 - What to do with changes that are needed
Domain
Product Backlog Management