## Sheet1
Question 1
At the moment, the engineering branch of your company is organized in siloed teams that specialize according to function (for example, design, front-end, back-end, database, and testing). What factors do you think are important to consider while transitioning from component teams to feature teams? (choose 2)
It is impossible to do Scrum without feature teams. Do not try to adopt Scrum until teams are reorganized into feature teams.
With feature teams, it is easier to calculate and compare the productivity per team. Incentives on productivity are likely to speed up the transition to feature teams and, therefore the adoption of Scrum.
Feature teams will require time to become productive as people from the different layers and components become accustomed to working and delivering unified functionality together as one Scrum Team.
Productivity, in terms of lines of code or story points, will probably suffer during the transition, although even then delivery of business value is still likely to increase.
Resources
Q6 - Siloed Teams
Domain
Scrum Teams
Question 2
During the Sprint Retrospective, the Product Owner raised a concern that the Developers only just met the Sprint Goal for the last Sprint. Developers think that the cause of the problem might be that some of them were working on other projects at the same time and that delayed the work. Which Scrum value were they not following? (choose 1)
Commitment
Courage
Focus
Respect
Openness
Resources
Q6 - Only just meeting the Sprint Goal
Domain
Scrum Values
Question 3
At the Sprint Retrospective the Scrum Team are addressing the quality difficulties that prevented completing an appropriate Increment at Sprint end. However, the Developments did indicate that they were able to accomplish a high velocity. Which two of these responses would you think their Scrum Master is best to take? (choose 2)
Acknowledge the hard work but remind the Developers that they need to improve in order to do even more in the next Sprint.
Agree and acknowledge the team’s hard work, so they will be motivated to do even more in the next Sprint.
Stress the value of working software over measured velocity
Facilitate a discussion on how to improve the quality to a level high enough for the Increment to be releasable, even if the measured velocity drops in the next Sprint.
Resources
Q3 - High velocity but Sprint Goal not met
Domain
Done
Question 4
A key and very senior stakeholder directly asks a particular developer to add a piece of functionality to the sprint backlog now as an urgent task, is it disrespectful to refuse to add the functionality immediately? (choose 1)
Yes
No
Resources
Q2 - Pressure from Stakeholder
Domain
Scrum Values
Question 5
How does Scrum apply Empiricism? (choose 3)
All the artifacts are immutable, they do not change for clarity.
Scrum Artifacts help with transparency.
The accountabilities are inspected and adapted in every event.
During each Scrum Event, decisions are made on one or more artifacts.
Scrum is based on Lean thinking, which is empiricism.
One or more artifacts are inspected in each event.
Resources
Q4 - How does Scrum apply Empiricism?
Domain
Empiricisum
Question 6
Which two items best describe what ‘done’ means? (choose 2)
Having an Increment of working software that is potentially releasable to the end users.
All the work completed within the current skills of the Developers.
All the work performed as defined in the Definition of Done.
All the work needed to prepare the Increment for testing.
Resources
Q6 - What does Done mean?
Domain
Done
Question 7
Once born, who in the Scrum team can update or change an increment? (choose 1)
The Developers
The Product Owner
The Scrum Master
Senior Developers
Release Management
Resources
Q4 - When an increment is born, and who can edit it?
Domain
Scrum Artifacts
Question 8
After a recent Sprint Review some of the stakeholders felt that the information presented was too fast and they didn’t get chance to go into the depth that they felt they needed to. The meeting had to finish because it ended at the end of the business day. The stakeholders ask the Scrum Master to hold a follow up Sprint Review and extend the future Sprint Reviews. What should the Scrum Master do? (choose 2)
Coach the Developers with time management techniques and how to present the key information the Stakeholders need.
Schedule the next Sprint Review an hour earlier so that the event can be extended if necessary.
Invite the stakeholders to a Sprint Review Part 2 meeting.
Coach the stakeholders to understand Scrum and that all events are timeboxed and should not be extended, however they will discuss the timebox of the Sprint Review in the Sprint Retrospective and see if it can be extended for future Sprints. In the meantime help the Scrum Team to interact more with the stakeholders throughout the Sprint.
Overall explanation
The Scrum guide says the Sprint Review "is timeboxed to a maximum of four hours for a one-month Sprint. For shorter Sprints, the event is usually shorter." As the Sprint should never be longer than a month, we can deduce that the maximum a Sprint Review should be is 4hrs. It is always best if the Scrum team can learn to manage time better and present key information in the time allotted. However, the Sprint Review is there to make improvements for future Sprints, so this situation should certainly be discussed. If the Sprint Review is too short and then it makes sense to make future ones longer, so long as they aren't so long that they break the Scrum Guide guidelines.
Resources
Q6 - Sprint Review too fast - a cross-functional team
Domain
Coaching and mentoring
Question 9
The Developers have realized that it does not possess the necessary tools and infrastructure to complete each of the items chosen from the Product Backlog. What action would you recommend as the Scrum Master? (choose 1)
Coach the Developers to improve its skills, tools and infrastructure over time and establish a Definition of “Done” that is actually possible to achieve given the current circumstances.
Stop the Sprint and have the Developers work on the infrastructure before continuing.
Encourage the Product Owner to accept partially done Increments and complete the work in the Hardening Sprint.
Resources
Q7 - When the developers don't have the skills and tools
Domain
Coaching and mentoring
Question 10
What is the first event of the Sprint? (choose 1)
Daily Scrum
Backlog Refinement
Sprint Retrospective
Sprint Planning
Sprint Review
Resources
Q1 - First Event of the Sprint
Domain
Scrum Events
Question 11
How should a Scrum Master divide a group of 50 people into multiple scrum teams? (choose 1)
Ask the developers to divide themselves into teams.
Create teams based on the functional layer they are working on.
Create teams based on the health of the working relationship of the team members.
Resources
Q4 - Splitting a big group into Scrum Teams
Domain
Scrum Teams
Question 12
Developing new or revising existing technical documentation is a requirement of the team's Definition of Done. This is done to ensure that the product and/or its features can be maintained in the future. During the Sprint, the team's technical writer will be on holiday. What action should you take? (choose 1)
Delay the documentation for the technical writer’s return and create a backlog of work to be handled in one technical writing sprint.
The Scrum Team is still accountable to meeting the Definition of Done, the Developers should write the documentation, they are best placed to do so as the developers of the product.
Tell the developers to form a specialist team of technical writers to work on documentation for this product and any others in the company.
Resources
Q8 - Documentation in the Definition of Done
Domain
Done
Question 13
What is the best description of the Definition of Done? (choose 3)
At Sprint Planning it guides the Developers when creating a forecast for items.
It creates transparency of the state of the Increment for inspection at the Sprint Review.
It serves as a checklist to inspect whether the Developers have performed all their tasks by the Sprint end.
It helps the Developers identify the work remaining for an Increment to be ready for release.
It serves to track how much of a Product Backlog item is completed during the Sprint.
Resources
Q1 - Description of Definition of Done
Domain
Done
Question 14
What questions should be answered during the Daily Scrum? (choose 1)
What did I do yesterday and what do I plan to do today?
None of these questions.
Both of these questions.
Do I see any impediment that prevents the Developers or me from meeting the Sprint Goal?
Resources
Q3 - Daily Scrum Questions
Domain
Scrum Events
Question 15
By the end of the Sprint, a Product Backlog item in the Sprint Backlog does not meet the team's Definition of Done. What two things should happen with the item? (choose 2)
Review the item, add the done part to the Increment. Estimate the remaining work and add that to the Product Backlog.
It will be inspected at the Sprint Review and if it is acceptable by the stakeholders then include it in the Increment.
Do not include the item in the Increment for the Sprint.
Estimate the remaining work needed to make it "done" and add it to the Product Backlog for the Product Owner to decide what to do with it.
Resources
Q7 - What to do if Definition of Done is not met
Domain
Done
Question 16
During a Daily Scrum 2 developers disagree on a task and get into a heated argument, what Scrum Value are they not showing? (choose 1)
Courage
Respect
Openness
Focus
Commitment
Resources
Q1 - A heated argument
Domain
Scrum Values
Question 17
You are a Scrum Master of a 9 member Scrum Team; you haven't joined the Daily Scrum for some time because you thought it was running well. However, you join today and notice it took 20 minutes. The Developers often go over 15 minutes and they propose dividing the Scrum Team into two cohesive groups with their own Daily Scrum. What is your response? (choose 1)
You agree. If the Daily Scrum becomes too long, the team should consider reorganizing into multiple cohesive Scrum Teams, each focused on the same Product and Product Backlog.
You offer to join the Daily Scrum and teach them to keep the Daily Scrum within a 15-minute timebox.
You say that it is common and reasonable to extend the Daily Scrum. The 15 minute rule is just a guideline.
Resources
Q7 - Daily Scrum running over
Domain
Scrum Values
Question 18
The Product Owner is concerned about the slow progress of releases and thinks the Definition of Done should be reduced to speed up progress. As the Scrum Master what would you advise? (choose 4)
Advise seeking the stakeholder’s permission by informing them that reducing the Definition of Done will lead to more frequent releases and greater velocity.
Accept the decision as a mutual agreement has been made between the Developers and the Product Owner.
Reducing the Definition of Done will introduce technical debt such as unknown errors as functionality is added. The product might become more difficult to stabilize as work progresses. Development for future releases is likely to be slowed down in unpredictable ways.
Releasing the version with a reduced Definition of Done creates false assumptions about the actual state of the system and is risky. Fixes may need to be added post-release impacting user experience, reputation and development progress.
Ask the Developers and the Product Owner what problem they are trying to solve by reducing the Definition of Done. In what ways will this decision impact transparency and quality?
Ask the Developers and the Product Owner if they are still able to produce releasable Increments by altering the Definition of Done.
Resources
Q4 - Reduction of Definition of Done bad practice
Domain
Done
Question 19
In Scaled Scrum should Scrum teams working on the same Increment have the same Start and End date? (choose 1)
No
Yes
Resources
Q9 - Scaled Scrum start and end dates of Sprints
Domain
Self-management
Question 20
During a Daily Scrum 2 developers disagree on a task and get into a heated argument, what are the best things a Scrum Master should do? (choose the 2 best answers)
Help create the environment and space to discuss conflicts, find agreements in a productive and positive way. Remind the other members of the Scrum Team that conflicting ideas are natural, but making it personal does not help.
Don't handle problems for the team. Instead, assist them in identifying and resolving issues on their own.
Try to move the team members away from each other to avoid further conflict as soon as possible to be productive.
Talk with each team member to understand why they have differences. Report them to their managers if they cannot solve their differences.
Wait till the Sprint Retrospective and show the importance of not wasting time in conflict, concentrating on work, and improving performance.
Resources
Q5 - Self-management to solve team disagreements
Domain
Self-management
Question 21
The Sprint Review often overruns resulting in many stakeholders needing to leave before the end of the meeting and missing key information. The stakeholders request to have a follow-up meeting the next day. As a Scrum Master how would you handle this situation? (choose 2)
Coach the stakeholders to understand Scrum and that all events are timeboxed and should not be extended.
Coach the Developers with time management techniques and how to present the most valuable functionalities first.
Split the Sprint Review into 2 parts and continue the Sprint Review the next day.
Schedule the Sprint Review an hour earlier than usual so that the event can be extended if necessary.
Coach the Product Owner to send an email to the stakeholders with a list of items that have been "Done" and what has not been "Done" before the Sprint Review to save time.
Resources
Q2 - Over running the Sprint Review
Domain
Coaching and mentoring
Question 22
Should the Definition of Done include testing? Choose the best answer
Yes testing is mandatory to ensure the increment is ready to be released.
It’s not mandatory, it’s up to the organisation and the Scrum team to decide on the Definition of Done.
Resources
Q9 - Should the Definition of Done include testing?
Domain
Done
Question 23
When it comes to completing all the items in the Sprint Backlog, all the Product Backlog Items added to the Sprint Backlog must be done by the end of the Sprint? (choose 1)
FALSE
TRUE
Resources
Changing Defo of Done & Q5 - Should all items be done by Sprint End?
Question 24
You have a choice of ways and locations to hold the Daily Scrum, how do you decide what option is best? (choose 1)
It should be held in a secluded area of the office so not to disturb others.
It should be held in a room where management cannot overhear.
It should be held wherever the Developers think is best.
It should be held wherever you can get on that particular day.
It should be held around the Scrum board.
Resources
Q7 - Who chooses the Daily Scrum location?
Domain
Scrum Events
Question 25
What is Scrum Based on? (choose 2)
A Defined Process
Lean thinking
A Hybrid Model
Empiricisum
A Complex Process
Resources
Q1 - What is Scrum based on?
Domain
Empiricisum
Question 26
After discussions you as the Scrum Master have convinced them that they need to have the Daily Scrum every day, but this still does not solve the problem of the trouble in hosting these meetings. As the Scrum Master what should you do? (choose the best answer)
Mandate the use of tools used elsewhere in the organisation that have helped other teams who are in different locations
Divide the Developers into subteams per location.
You as the Scrum Master are responsible for setting up the meetings.
Bring up the topic for discussion and allow the Developers to determine for themselves what to do as a self­ managing team.
Cause the removal of this impediment by informing management and challenge the distributed nature of the team
Tell the Developers to alternate who attends.
Resources
Q5 - Where to have the Daily Scrum
Domain
Scrum Events
Question 27
It's important that product development teams be cross-functional and comprised of people with a wide range of expertise to succeed. When implementing Scrum, what are the benefits of maintaining the existing component teams (for example, design, database, backend, and frontend)? (choose 1)
Component teams would have all the skills needed to deliver an increment of value
Because they have been working together for some time, there will be less initial disruption than a newly formed team. As they begin working, they will discover what works best and how to move towards cross-functional teams
There is less communication overhead than working in feature teams
Because their productivity is already predictable, they can deliver more valuable Increments than a newly formed team
Resources
Q7 - Component team short term pros
Domain
Scrum Teams
Question 28
Who plans the work during the Sprint? (choose 1)
The Developers
The Scrum Master
The Product Owner
The Senior Developers
Resources
Q1 - who plans the work?
Domain
Self-management
Question 29
You are a Scrum Master for three Scrum Teams who are all working on the same Product. Management wants to measure the velocity of all three teams so that they know which teams are working well and which teams may benefit from more assistance. What are your best responses? (choose 2)
Standardizing velocity across teams is a good way to understand which teams are producing the most value.
Providing incentives based on velocity can increase the Scrum Team’s motivation to produce more value.
Velocity is the amount of business functionality that a particular Scrum Team creates in a Sprint. It is unique to that team and used to forecast work in Sprint Planning.
There is no direct relationship between velocity and value. Value of the increment to the stakeholders is measured in other ways.
Resources
Q2 - Proper use of velocity
Domain
Done
Question 30
Which of these answers is a good sign the team is self-managing. (choose the 2 best answers)
The Developers are able to resolve internal conflicts between members in order to continue working.
The Developers are cross-functional and know what they need to do to complete all tasks committed to in Sprint Planning
Management is able to know which members are working on which items.
Creativity thrives and new possibilities are explored.
Resources
Q4 - Signs a team is Self-managing
Domain
Self-management